## Document Control
NorthBridge Technology Solutions Inc.
ISMS Risk Register — Document Control
Document Title | Information Security Risk Register
Document ID | NB-ISMS-004
Version | 1.0
Date | 2026-05-16
Author | Ashkon Irani
Reviewed By | IT Director
Approved By | Chief Executive Officer
Classification | Confidential
Review Frequency | Quarterly / Following any P1 or P2 Security Incident

## Risk Register
NorthBridge Technology Solutions Inc. — Information Security Risk Register (NB-ISMS-004)
Risk ID | Risk Title | Asset ID | Asset Name | Threat Category | Vulnerability | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Score | Inherent Risk Level | Current Controls in Place | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Level | Treatment Option | Treatment Action | Risk Owner | Target Completion | Status | Notes / Evidence
RSK-001 | Ransomware Attack via Phishing Email | AST-001 | Employee Laptops | Malicious External Actor | Unpatched endpoint software; insufficient email filtering; no EDR solution deployed | 5 | 5 | 25 | Critical | Basic antivirus in place. Annual security awareness training. Microsoft Defender enabled. | 3 | 5 | 15 | High | Mitigate | Deploy enterprise EDR solution (CrowdStrike or Sentinel One). Implement Microsoft Defender for Endpoint. Enable advanced email filtering with sandboxing. Increase phishing simulation frequency to quarterly. | IT Director | Q2 2025 | In Progress | Ransomware targeting government contractors has increased 340% since 2022 (CCCS Annual Report). Protected B data exposure would trigger mandatory GoC client notification.
RSK-002 | Unauthorized Access to Protected B Client Data | AST-007 | GoC Client Project Data | Malicious External Actor / Malicious Insider | Excessive user permissions; lack of role-based access control; no privileged access management | 4 | 5 | 20 | Critical | Azure AD authentication in place. Basic user account management process exists. | 2 | 5 | 10 | Medium | Mitigate | Implement Privileged Access Management (PAM) solution. Conduct quarterly access rights reviews. Enforce principle of least privilege across all Azure environments. Implement just-in-time access for administrative roles. | IT Director | Q1 2025 | In Progress | Linked to ISO 27001:2022 Controls 5.15, 5.16, 5.18, 8.2. Any breach of Protected B data must be reported to the GoC client within 24 hours per contract terms.
RSK-003 | Cloud Misconfiguration Exposes Client Data | AST-013 | Microsoft Azure Production Environment | Accidental Insider / Malicious External Actor | No enforced cloud security baseline; insufficient configuration change management; lack of automated misconfiguration detection | 4 | 5 | 20 | Critical | Azure Security Centre enabled. Manual configuration reviews conducted ad hoc. | 2 | 4 | 8 | Medium | Mitigate | Enable Microsoft Defender for Cloud with all policies set to Enforce. Implement Azure Policy to enforce security baseline. Deploy automated misconfiguration scanning (Prisma Cloud or equivalent). Require change management approval for all production environment changes. | IT Director | Q1 2025 | Not Started | Cloud misconfiguration is the leading cause of cloud data breaches globally (Gartner 2024). Canada East region confirmed for all client data per data residency requirements.
RSK-004 | Loss or Theft of Laptop Containing Confidential Data | AST-001 | Employee Laptops | Physical and Environmental | Full-disk encryption not enforced on all devices; no verified remote wipe procedure | 3 | 4 | 12 | Medium | MDM enrollment via Intune in place for most devices. BitLocker enabled on managed devices. | 1 | 3 | 3 | Low | Mitigate | Enforce full-disk encryption (BitLocker) via Intune policy for 100% of enrolled devices. Validate remote wipe procedure quarterly. Implement device compliance policy that blocks access to corporate resources if encryption is not confirmed. | IT Manager | Q1 2025 | In Progress | 15 laptops reported lost or stolen in the past 3 years. No data confirmed compromised to date due to partial encryption controls. Residual risk acceptable once full enforcement achieved.
RSK-005 | Credential Compromise via Phishing (No MFA) | AST-004 | Microsoft 365 Tenant | Social Engineering | Multi-factor authentication not enforced across all Microsoft 365 accounts; no Conditional Access policies | 5 | 4 | 20 | Critical | Password complexity policy enforced. Some accounts have MFA enabled voluntarily. | 2 | 4 | 8 | Medium | Mitigate | Enforce MFA for all Microsoft 365 accounts via Conditional Access policy within 30 days. Block legacy authentication protocols. Implement Conditional Access policies requiring compliant device and MFA for all cloud application access. | IT Manager | 30 Days | Critical — Immediate Action | Linked to POL-003 Access Control Policy. Business email compromise via credential theft is the most common attack vector against Canadian organizations (CCCS 2024). This risk is currently rated Critical and requires immediate escalation.
RSK-006 | Insider Exfiltration of Source Code | AST-009 | Source Code Repositories | Malicious Insider | Insufficient Data Loss Prevention controls; no automated monitoring of repository access patterns; inadequate offboarding process | 3 | 5 | 15 | High | Azure DevOps access requires authentication. Basic access logging enabled. | 2 | 4 | 8 | Medium | Mitigate | Implement DLP policy for source code repositories. Enable Azure DevOps audit logging and configure alerts for anomalous access patterns (bulk downloads, off-hours access). Formalize offboarding procedure to revoke all repository access within 4 hours of termination. | Development Lead | Q2 2025 | Not Started | Source code represents NorthBridge's primary intellectual property. Exfiltration to a competitor or hostile actor would be catastrophic. Government clients also have contractual interest in supply chain security of deployed code.
RSK-007 | Third-Party Vendor Breach Affecting NorthBridge Data | AST-008 | Employee HR Records | Third-Party and Supply Chain | No formal vendor risk assessment process; no security requirements in vendor contracts; BambooHR stores employee PII in US jurisdiction | 4 | 4 | 16 | High | BambooHR standard contractual terms in place. No formal security assessment has been conducted. | 2 | 3 | 6 | Low | Mitigate | Implement formal vendor risk assessment program per POL-005. Conduct immediate security assessment of BambooHR and all Tier 1 vendors. Add security addendum to all vendor contracts. Conduct Privacy Impact Assessment for US-hosted HR data under PIPEDA. | HR Manager / IT Director | Q2 2025 | Not Started | PIPEDA requires NorthBridge to ensure third parties protect personal information to an equivalent standard. US data hosting creates cross-border transfer obligations. Vendor risk program is a gap identified in ISMS implementation.
RSK-008 | Extended Outage of Azure Production Environment | AST-013 | Microsoft Azure Production Environment | Technical Failure / Malicious External Actor | No tested disaster recovery plan; single-region deployment for some workloads; RTO and RPO not formally defined | 3 | 5 | 15 | High | Azure Canada Central configured as secondary region. No DR plan documented or tested. | 2 | 4 | 8 | Medium | Mitigate | Document formal Business Continuity and Disaster Recovery plan. Define RTO and RPO for each critical workload. Configure active-active or active-passive failover for all Tier 1 client workloads. Conduct annual DR test with documented results and lessons learned. | IT Director | Q3 2025 | Not Started | GoC client contracts specify minimum uptime SLAs. Unplanned outage exceeding SLA triggers financial penalties and potential contract review. Azure Canada East has had 3 significant outages in 2024 per Microsoft Service Health dashboard.
RSK-009 | Phishing Attack Leading to BEC (Business Email Compromise) | AST-004 | Microsoft 365 Tenant | Social Engineering | Insufficient email security controls; DMARC/DKIM/SPF not fully configured; staff not trained to identify BEC patterns | 4 | 4 | 16 | High | Basic spam filtering enabled. Annual awareness training conducted. | 2 | 3 | 6 | Low | Mitigate | Implement DMARC, DKIM, and SPF email authentication. Configure Microsoft Defender for Office 365 Plan 2 with anti-phishing policies. Deploy impersonation protection for executive email addresses. Increase phishing simulation frequency and add BEC-specific training module. | IT Manager | Q2 2025 | Not Started | BEC attacks cost Canadian organizations $53M in 2023 (RCMP). Finance team wiring processes must include dual-approval controls as compensating control.
RSK-010 | Unauthorized Physical Access to Server Room | AST-019 | Server Room — Ottawa HQ | Physical and Environmental | Server room access not logged electronically; no CCTV coverage inside server room; visitor escort policy not enforced | 2 | 4 | 8 | Medium | Keycard access system on server room door. Access limited to IT team. | 1 | 3 | 3 | Low | Mitigate | Install CCTV camera inside server room with 90-day retention. Implement electronic access logging with review process. Enforce visitor escort policy for all non-IT personnel. Conduct quarterly physical security review. | Operations Manager | Q2 2025 | Not Started | Physical access to server room enables direct access to network infrastructure, bypassing all logical security controls. Keycard access logs currently stored only on the physical access control system with no integration to SIEM.
RSK-011 | Privileged Account Compromise via Stolen Admin Credentials | AST-010 | IT Administrator Credentials | Malicious External Actor / Malicious Insider | Admin credentials stored in shared password manager; no dedicated Privileged Access Workstation; admin accounts used for daily tasks | 3 | 5 | 15 | High | 1Password Teams deployed. MFA enabled for password manager access. | 2 | 4 | 8 | Medium | Mitigate | Implement dedicated Privileged Access Workstations (PAWs) for all administrative tasks. Enforce separate admin accounts distinct from daily-use accounts. Implement session recording for all privileged sessions. Review admin account list quarterly and remove unnecessary access. | IT Director | Q2 2025 | Not Started | Compromise of admin credentials provides complete access to all NorthBridge and client systems. This risk is treated as Critical in the inherent state due to the catastrophic impact of full administrative compromise.
RSK-012 | Failure to Notify GoC Client of Security Incident Within SLA | AST-007 | GoC Client Project Data | Regulatory and Legal | No documented incident notification procedure; incident severity classification not formally defined; client notification contacts not maintained | 3 | 4 | 12 | Medium | Incident Response Policy (POL-004) drafted but not formally approved or communicated. | 1 | 3 | 3 | Low | Mitigate | Finalize and communicate Incident Response Policy (POL-004). Document client notification contact lists for all active GoC contracts. Conduct tabletop exercise simulating a Protected B data breach with notification timeline. Implement 24-hour on-call escalation procedure for IT Director. | IT Director | Q1 2025 | In Progress | GoC contracts typically require notification within 1-24 hours of a confirmed incident. Failure to notify within SLA constitutes a contract breach and may result in termination. Linked to POL-004.
RSK-013 | Unpatched Software Vulnerability Exploited by Attacker | AST-001 | Employee Laptops | Malicious External Actor | No formal patch management process; patch compliance not monitored; critical patches not prioritized | 4 | 4 | 16 | High | Windows Update enabled on most devices. No centralized patch monitoring or compliance reporting. | 2 | 3 | 6 | Low | Mitigate | Implement centralized patch management via Microsoft Intune. Define patch SLAs: Critical patches within 48 hours, High within 7 days, Medium within 30 days. Generate monthly patch compliance reports for IT Director review. Extend patch management to cover all third-party applications. | IT Manager | Q2 2025 | Not Started | Unpatched vulnerabilities account for 60% of confirmed breaches (Verizon DBIR 2024). Patch management is a foundational control and a mandatory requirement under most GoC security frameworks.
RSK-014 | Developer Introduces Vulnerability into Government-Deployed Code | AST-009 | Source Code Repositories | Accidental Insider | No mandatory security code review; no automated static analysis security testing (SAST) in CI/CD pipeline; developers not trained in secure coding practices | 3 | 5 | 15 | High | Peer code review required for all pull requests. No automated security scanning. | 2 | 4 | 8 | Medium | Mitigate | Integrate SAST tooling (Semgrep or Checkmarx) into Azure DevOps CI/CD pipeline. Require security scan results as a gate before merge to main branch. Provide OWASP Top 10 secure coding training to all developers annually. Add security-focused code reviewer designation for high-risk changes. | Development Lead | Q2 2025 | Not Started | A vulnerability introduced into government-deployed software could affect federal systems and constitute a supply chain security incident. Linked to RSK-006 and GoC supply chain security requirements.
RSK-015 | Employee Data Breach via HR System (PIPEDA Non-Compliance) | AST-008 | Employee HR Records | Third-Party and Supply Chain / Regulatory and Legal | No Privacy Impact Assessment conducted for US-hosted HR data; no data processing agreement with PIPEDA-compliant terms | 3 | 4 | 12 | Medium | BambooHR standard terms reference SOC 2 compliance. No PIPEDA-specific addendum in place. | 2 | 3 | 6 | Low | Mitigate | Conduct Privacy Impact Assessment for BambooHR data processing. Add PIPEDA-compliant data processing addendum to vendor contract. Evaluate feasibility of migrating to a Canadian-hosted HR solution. Appoint Privacy Officer responsible for PIPEDA compliance oversight. | HR Manager | Q3 2025 | Not Started | PIPEDA requires meaningful consent and equivalent protection for personal information transferred outside Canada. Canada's Bill C-27 (when enacted) will impose stricter requirements. Non-compliance can result in OPC investigation and reputational damage.
RSK-016 | Loss of Key IT Staff During Security Incident | AST-016 | IT Administrator Team | Technical Failure | Single points of knowledge in IT team; no documented runbooks for critical recovery procedures; no succession plan for IT Director role | 2 | 4 | 8 | Medium | Small IT team with some cross-training. No formal runbooks documented. | 1 | 3 | 3 | Low | Mitigate | Document runbooks for all critical recovery and incident response procedures. Cross-train minimum two IT staff on all critical administrative functions. Establish relationship with external Managed Security Service Provider (MSSP) for surge capacity. Include IT succession planning in annual HR review. | IT Director | Q3 2025 | Not Started | During a major incident such as ransomware, the simultaneous unavailability of key IT staff (illness, resignation, compromise of accounts) would severely impair response capability. Runbook documentation is a low-cost high-impact control.
RSK-017 | Sensitive Data Sent to Wrong Email Recipient | AST-004 | Microsoft 365 Tenant | Accidental Insider | No DLP policies configured in Microsoft 365; no email recipient confirmation prompts for external addresses; staff not trained on data handling procedures | 4 | 3 | 12 | Medium | Basic email filtering in place. No DLP controls deployed. | 2 | 2 | 4 | Low | Mitigate | Implement Microsoft Purview DLP policies to detect and block transmission of Protected B data outside approved domains. Enable external recipient warning prompts in Outlook. Conduct data handling training focused on email as part of annual awareness program. | IT Manager | Q2 2025 | Not Started | Misdirected email is one of the most common causes of personal data breaches reported to the OPC. For GoC clients, any transmission of Protected B data to an unauthorized recipient constitutes a reportable incident.
RSK-018 | Failure of Backup System Leading to Unrecoverable Data Loss | AST-013 | Microsoft Azure Production Environment | Technical Failure | Backup completion not monitored; recovery procedures not tested; backup retention policies not formally defined | 3 | 4 | 12 | Medium | Azure Backup configured for most production workloads. No recovery testing conducted. | 1 | 3 | 3 | Low | Mitigate | Define formal backup policy including retention periods, recovery point objectives (RPO), and responsible parties. Implement automated backup monitoring with alerting on failures. Conduct quarterly backup recovery tests with documented results. Ensure all critical workloads are covered by backup policy. | IT Manager | Q2 2025 | Not Started | An unmonitored backup that silently fails provides a false sense of security. Recovery testing is the only way to confirm backups are usable. Linked to RSK-008 (DR plan).
RSK-019 | Regulatory Non-Compliance with ITSG-33 Requirements | AST-007 | GoC Client Project Data | Regulatory and Legal | ITSG-33 control implementation not formally documented; no compliance monitoring process; gaps between current state and required controls not assessed | 3 | 4 | 12 | Medium | Awareness of ITSG-33 requirements. No formal gap assessment or compliance tracking in place. | 2 | 3 | 6 | Low | Mitigate | Conduct formal ITSG-33 gap assessment against all active GoC contract security requirements. Document control implementation status for each required ITSG-33 control. Implement quarterly compliance monitoring review. Assign dedicated GRC resource to maintain ongoing compliance tracking. | IT Director | Q2 2025 | Not Started | ITSG-33 compliance is a contractual obligation under all NorthBridge GoC contracts. Non-compliance identified during a client security audit could result in contract suspension pending remediation. This risk directly supports the business case for the ISMS implementation.
RSK-020 | VPN Compromise Enabling Network-Level Access | AST-005 | VPN Client and Infrastructure | Malicious External Actor | VPN firmware not kept current; no monitoring of VPN session anomalies; VPN credentials not subject to MFA | 4 | 5 | 20 | Critical | Cisco AnyConnect deployed. Password authentication in place. | 2 | 4 | 8 | Medium | Mitigate | Enforce MFA for all VPN connections. Implement certificate-based authentication as primary VPN authentication method. Establish VPN firmware update schedule (monthly). Configure SIEM alerting for anomalous VPN session patterns (off-hours, unusual geolocation, concurrent sessions). | IT Manager | Q1 2025 | Not Started | VPN compromise provides an attacker with network-level access equivalent to being on the internal network. With remote employees accessing GoC client environments via VPN, a VPN compromise directly threatens Protected B data. This is a Critical inherent risk.
RSK-021 | Inadequate Security Awareness Leading to Repeated Incidents | AST-016 | IT Administrator Team | Accidental Insider | Annual training only; no phishing simulations; no metrics tracked for training effectiveness; new employees not trained before system access | 4 | 3 | 12 | Medium | Annual security awareness training delivered. Completion tracked by HR. | 2 | 2 | 4 | Low | Mitigate | Increase training frequency to role-based modules quarterly. Implement phishing simulation program with immediate remediation training for failures. Track and report metrics: phishing click rates, training completion, repeat offenders. Require training completion before system access is granted to new employees. | HR Manager | Q2 2025 | Not Started | Human factors contribute to over 80% of security incidents (IBM Cost of Data Breach 2024). Security awareness is a foundational control that improves the effectiveness of all other technical controls by reducing the likelihood of social engineering success.
RSK-022 | Uncontrolled Use of Personal Cloud Storage for Work Files | AST-007 | GoC Client Project Data | Accidental Insider | No policy prohibiting use of personal cloud storage; no DLP controls to detect unauthorized uploads; staff convenience drives shadow IT behaviour | 4 | 4 | 16 | High | Acceptable Use Policy drafted but not formally approved or widely communicated. | 2 | 3 | 6 | Low | Mitigate | Finalize and communicate Acceptable Use Policy (POL-002). Implement Microsoft Defender for Cloud Apps (CASB) to detect and block uploads to unauthorized cloud storage. Configure DLP policy to prevent Protected B data leaving approved Microsoft 365 environment. | IT Manager | Q2 2025 | Not Started | GoC contracts prohibit storage of Protected B data in unauthorized cloud environments. Personal Google Drive, Dropbox, and iCloud do not meet GoC security requirements. CASB deployment provides both detection and prevention capability.
RSK-023 | Power Failure Causing Extended Outage of Ottawa HQ | AST-018 | Ottawa HQ — 350 Sparks Street | Physical and Environmental | UPS provides only 15-minute runtime; no generator on site; business continuity plan for extended facility outage not documented | 2 | 3 | 6 | Low | UPS in place for server room. Generator not available. | 1 | 2 | 2 | Low | Accept | Formally accept residual risk given primarily cloud-based architecture. Document acceptance with IT Director approval. Review annually. Consider generator feasibility assessment in FY2026 capital planning. | Operations Manager | Q3 2025 | Accepted — IT Director Approval Required | Given NorthBridge's primarily cloud-based architecture, an extended HQ power outage does not prevent remote employees from continuing to work. Residual impact is limited to on-site staff productivity and server room hardware. Risk accepted pending IT Director written approval.
RSK-024 | Expired or Misconfigured TLS Certificates Causing Service Disruption | AST-013 | Microsoft Azure Production Environment | Technical Failure | No certificate inventory maintained; no automated certificate expiry monitoring; manual renewal process prone to oversight | 3 | 3 | 9 | Medium | Certificates managed manually. Renewal reminders set in calendar by IT Manager. | 1 | 2 | 2 | Low | Mitigate | Implement automated certificate management via Azure Key Vault with expiry alerting at 60 and 30 days. Maintain certificate inventory in Asset Register. Migrate all eligible services to automated certificate renewal. | IT Manager | Q2 2025 | Not Started | Certificate expiry is a common cause of service disruptions and has affected major organizations including large banks and government services. Automated management eliminates this risk at low cost.
RSK-025 | Insufficient Logging and Monitoring — Delayed Breach Detection | AST-013 | Microsoft Azure Production Environment | Malicious External Actor | No SIEM deployed; security logs not centrally aggregated; no defined log retention policy; no alerts configured for suspicious activity patterns | 4 | 4 | 16 | High | Individual service logs available in Azure Monitor. No centralized monitoring or alerting. | 2 | 3 | 6 | Low | Mitigate | Deploy Microsoft Sentinel as SIEM solution. Onboard all critical log sources: Azure AD, Azure activity logs, Microsoft 365, VPN, endpoint EDR. Define detection rules for priority threats (credential stuffing, lateral movement, large data transfers). Define log retention policy, minimum 90 days hot, 1 year cold storage. Assign Tier 1 monitoring responsibility. | IT Director | Q3 2025 | Not Started | The average dwell time for attackers in Canadian organizations is 197 days (IBM 2024), meaning breaches go undetected for over 6 months on average. Without a SIEM, NorthBridge has no systematic way to detect an active breach. This control is foundational to the entire security monitoring capability.

## Summary Dashboard
NorthBridge Technology Solutions Inc. — Risk Register Summary Dashboard
NB-ISMS-004 v1.0 ¦ Review Date: [Insert Date] ¦ Classification: Confidential
INHERENT RISK DISTRIBUTION (Before Controls)
Risk Level | Score Range | Count | % of Total | Colour | Action Required
Critical | 20–25 | 5 | 20% | Critical | Immediate escalation — treat within 5 days
High | 13–19 | 9 | 36% | High | Formal treatment plan within 30 days
Medium | 7–12 | 10 | 40% | Medium | Treatment plan within 90 days
Low | 1–6 | 1 | 4% | Low | Monitor annually — within risk appetite
RESIDUAL RISK DISTRIBUTION (After Existing Controls)
Risk Level | Score Range | Count | % of Total | Colour | Acceptance Status
Critical | 20–25 | 0 | 0% | Critical | NEVER Acceptable — immediate action required
High | 13–19 | 1 | 4% | High | Not Acceptable — formal treatment required
Medium | 7–12 | 8 | 32% | Medium | Conditionally Acceptable — IT Director approval
Low | 1–6 | 16 | 64% | Low | Acceptable — within NorthBridge risk appetite
TREATMENT OPTION DISTRIBUTION
Treatment Option | Count | % of Total | Description
Mitigate | 24 | 96% | Implement controls to reduce likelihood and/or impact
Transfer | 0 | 0% | Shift financial consequences to third party (insurance, contracts)
Accept | 1 | 4% | Formally document and accept residual risk within appetite
Avoid | 0 | 0% | Cease the activity that creates the risk
KEY METRICS
Total Risks Identified | 25
Risks Requiring Immediate Action (Critical Residual) | 0
Risks Requiring Treatment Plan (High Residual) | 1
Risks Within Appetite (Low Residual) | 16
Average Inherent Risk Score | 14.4
Average Residual Risk Score | 6.0
Risk Reduction Rate (Avg) | 58%

## Instructions
Risk Register — Instructions for Use
Purpose | This Risk Register documents all information security risks identified within the scope of NorthBridge's ISMS. It is the primary working document for risk management activities.
How to Score Risks | Use the methodology defined in NB-ISMS-003. Inherent Risk = Likelihood x Impact BEFORE controls. Residual Risk = Likelihood x Impact AFTER existing controls. All scoring criteria are defined in the methodology document.
Inherent vs Residual | Inherent risk is your baseline, what the risk would be with zero controls. Residual is what remains after your current controls are applied. Compare Residual against acceptance criteria (Section 8 of NB-ISMS-003).
Adding New Risks | Insert a new row in the Risk Register tab. Assign the next sequential Risk ID (RSK-026 etc). Link to the Asset ID from NB-ISMS-002. Complete all columns before saving.
Updating Existing Risks | After implementing a treatment action, update the Residual Likelihood, Residual Impact, and Residual Risk Score columns. Update Status to 'Complete'. Add evidence reference in the Notes column.
Status Values | Use: 'Not Started' / 'In Progress' / 'Complete' / 'Accepted — [Approver] Approval Required' / 'Critical — Immediate Action'
Review Schedule | Full register review: Annually. High/Critical risks: Monthly. Following any P1/P2 incident: Ad hoc review within 5 business days. Quarterly summary to IT Director.
Approval | Completed Risk Register must be reviewed by IT Director and presented to executive leadership at annual ISMS management review.